## Sheet1
| status | deadline
Feasibility |  | 10/16 | section 6, twinkle
Vision |  | 10/16
Project Plan |  | 10/16 | 9am-12pm
Domain Model |  | 10/16
UCD |  | 10/16
UC Prioritization |  | 10/16
OC - for most importants |  | 10/16 | 2pm
Supplementary Specification |  | 10/16 | after OC
Textual Descriptions |  | 10/16 | keerthi
Fully dressed - Place Order |  | 10/16 | check brief desc
SSD - Place Order |  | 10/16
Status Report |  | 10/16 | after
Meeting Notes |  | 10/16 | after
UI Sketches |  | 10/18
Logical view - tiered arch. |  | 10/18
Composite diagrams |  | 10/18
Presentation |  | 10/18
Proof of concept |  | 10/20 | ram
High-level Architecture |  | 10/20
UI Design (sketches) |  | 10/20
DB Design (tables) |  | 10/20
Status Report |  | 10/20
Meeting Notes |  | 10/20
System Detailed Design |  | 10/27
Initial Impl. - Place Order |  | 10/27
Demo - Place Order |  | 10/27
Status Report |  | 10/27
Meeting Notes |  | 10/27